## Sheet1
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-16 | Daniel Lee | P2 | resolved | Daniel | When the character collides with a platform wall, it is expected to bounce back in the opposite direction. Instead, the character is currently passing through the wall | Upon colliding with the side of a platform, the character should rebound in the opposite direction of the wall | The character does not bounce back when colliding with the platform's wall but instead continues through the wall as if no collision occurred. | 1. Position the character adjacent to a platform wall. 2. Move the character towards the platform wall. 3. Observe the character's behavior upon collision with the wall.
2 | 2024-02-16 | Daniel Lee | P2 | resolved | Allan | The character is expected to come to a stop upon death with no animations playing. However, currently, the character continues to move horizontally after death, indicating that horizontal velocity is not being reset. | When the character dies (for example, by being hit by a falling boulder), all movement and animations should cease. | After the character is hit and the death event is triggered, the character continues to slide horizontally. | 1. Allow the character to be hit by the boulder to trigger the death sequence. 2. Observe the character's behavior following the death event.
3 | 2024-03-24 | Brayden Shinkawa | P3 | resolved | Brayden | The character is expected to animate when moving immediately on input, however the movement inputs take an extra second to be noticed. The character will move but not animate for a second after input | When the character moves, the character should immediately start its running animation | The character takes an extra second after movement input to start its running animation. Releasing another key will also stop running animations | 1. Move the character 2. Observe the character not animate its movement in the first second of movement
4 | 2024-03-24 | Brayden Shinkawa | P2 | resolved | Aaron | When the character dies and the player continues drawing, the program should reset the scene. Instead, the game crashes | When the character dies and the game resets while the player's drawing, the game shouldn't crash | When the character dies and the game resets while the player's drawing, the game crashes | 1. Make the character die 2. While the character is dying, draw on screen 3. Keep drawing, game will crash
5 | 2024-03-24 | Joshua Chew | P3 | resolved | Joshua | When the character jumps or moves, the movement and jumping should be consistent across multiple machines. However, this is not the case | When comparing two machines running the game, both players should have similar jump heights and movement speeds | When comparing two machines running the game, players have differing jump heights and movement speeds | 1. Run the game on two different cpu setups 2. Compare jump height and speed of player 3. If different, problem is still present
6 | 2024-03-24 | Aaron Zhang | P4 | resolved | Joshua | When the character moves right and adds a short left movement, the player will continue to slide left even after the player stops pressing key inputs | When the character presses the A or D keys for moving left and right, they should move in their respective directions. If no keys are pressed, the player shouldn't move | Player continue moves without deaccelerating even when no input keys are pressed | 1. Make the character move right 2. Quickly press the left move button 3. Player should start sliding left without deaccelerating
7 | 2024-03-24 | Joshua Chew | P4 | resolved | Allan | When the player respawns at a checkpoint flag, the checkpoint sound continues to play | When the player respawns at the checkpoint flag, no checkpoint sound should occur | When the player respawns at the checkpoint flag, the checkpoint sound repeats instead of staying silent | 1. Get player to hit a checkpoint (sound should play) 2. Get player to respawn at checkpoint by pressing L 3. Checkpoint sound will continue to repeat as long as the player stands on the checkpoint
8 | 2024-03-24 | Brayden Shinkawa | P5 | resolved | Anyone | After the player dies in the running animation, they will be stuck in the running loop animation on respawn, even when not moving | When the player respawns, they should be in the neutral player texture frame | When the player respawns afer dying in a running loop animation, they are stuck in the running loop animation even when not moving | 1. Get player to respawn after dying while running 2. player randomly respawns in run animation
9 | 2024-04-08 | Joshua Chew | P3 | non-critical - fix after ship | Anyone | Player randomly teleports on collision with platform floor on very rare occasion | When the player collides with the platform floor (after falling or otherwise), they should be stopped and stand atop the platform | Player clips through the platform floor, then gets re-positioned by teleporting to the side edge of the platform | 1. Get the machine to run in a low-performant state (time between ticks increases) 2. Move (fall) onto the platform 3. Player gets teleported to the side of the platform
10 | 2024-04-08 | Brayden Shinkawa | P3 | non-critical - fix after ship | Anyone | Player sometimes gets stuck on the side of a drawn platform | When the player collides with a drawing, a collision should result in the stoppage of gravity only when the player is directly on top of it | Gravity stops the player on collision with just the side (endpoint) edge of a drawn line, resulting in a "stuck"-like effect | 1. Draw a line (horizontal for convenience) 2. Jump into the short edge of the line (at the endpoint). 3. The player gets "stuck". Able to "unstick" by moving in the opposite direction that it took to get stuck.